VRMouse

Chris Denniston
University of Missouri – Kansas City

Revision History
Author	Date	Revision
Chris Denniston	7/2/2016	Initial Release

Table of Contents

Vision Statement

Virtual Reality is an emerging trend in computing which has many applications. Virtual reality has so far been focused on transporting you to another world, generally in the form of a game or some sort of interactive piece of media. My project aims to instead focus on moving you to a different place and perspective in the real world in real time. I plan to devise a way to use low cost Virtual Reality to allow the control of a robot. This project mostly focuses on a way to reduce the latency of input and output such that any device with two cameras mounted on it and the ability to swivel could utilize this technology. This could allow people to visit far off locations, such as European museums or ancient temples, without having to leave their home by renting time on a robot inside the location. It could also be used to give remote tours of museums by having a course for a robot and only the cameras swivel around so people can look around at art like they would on a museum tour. This could also be sold as a children's toy for exploring around the house since the whole setup is fairly low cost, and parents generally own a smart phone. The goal of this project is to create a robot which may be remotely controlled through a Google Cardboard VR headset. The robot should look in the same spacial direction that the Cardboard is turned. This project doesn't necessarily include building a very advanced robot since it is mostly focused on the control side of it. It is essential that the robot responds to the movement of the VR headset and is easy to control using the headset but not necessarily as important that the system is wireless or will work well over long distances. It is very possible that the current infrastructure of Internet speeds is not able to support this for long distances but it should be able to on a local area network. This project will be for users who want to be transported to another location and have true interactivity with their environment through the use of Virtual Reality.

Requirements
This project only has one category of user and that is a robot operator. This will be a person who is using a Google Cardboard to control a robot. This person should not necessarily have any knowledge of robotics or virtual reality, but should be familiar enough with a Google Cardboard to operate one.

Actor	Goal
Robot Operator	Look around and have camera follow
	Be able to remotely connect to a running robot
	Be able to direct the robots movement
	Be able to configure distances such that the projection is correct in VR
	Be able to change settings of movement speed to match a desired latency.
	The system should make sense in a way that doesn't necessitate a tutorial.

## Product Backlog
The collection of stories makes up your project’s product backlog:

Story ID	Story	Story Points	Priority	Status
S1	Build robot to the point it's ready to be programmed	3	3
S2	As a robot operator, I would like Google Cardboard to display different streams in each eye so that I get proper 3d	5	1	C
S3	As a robot operator, I would like a way to input the addresses of the left and right streams	3	6
S4	As a robot operator, I would like the robot to use a low latency stream protocol so that I will get better feedback	4	2	C
S5	As a robot operator, I would like to be able to configure latency settings in order for more advanced users to get closer to their natural movement speed.	3	5
S6	As a robot operator, I would like the robot to turn to match where I am looking in space	4	3
S7	As a Robot operator I would like the location of the robot command server to be editable	1	7	C

Sprint #1

Estimated Velocity: 6
Sprint Backlog
Story ID	Story / Task	Estimated / Hours	Actual / Hours
S2	Find example of streaming a single stream on-line	3	1
	Read through Google Cardboard documentation for activity lifecycle	2	3
	Learn basics of OpenGL	5	4
	Find out how to render differently in each eye	3	6
	Find example stream using RTSP with relatively low latency	3	3
	Create code structure to modularize rendering and stream loading	1	1
	Load Streams asynchronously	1	1

## Iteration #1 Review Meeting
Learning OpenGL and the basics of Google cardboard took a while. Once I figured all that out a lot of the other parts just fell in together. It took me a bit of thinking on exactly how to render two different streams. The good news is this was the only part that I had basically no idea how to do from the get go and the rest of it I feel like I can more accurately plan because it's things that are close to things I have done before.
## Iteration #1 Retrospective

Everything in the sprint went pretty well. I learned a lot about the OpenGL/Google cardboard lifecycle and what components work together. I also learned that the documentation for OpenGL on android isn't quite there but still easy enough to figure out.

Project velocity: 3
A nice visual way of tracking velocity is to maintain a graph like the following:

6
5	x
4	x
3	x	x
2	X	x
1	X	x
	Sprint 1	Sprint 2	Sprint 3	Sprint 4	Sprint 5	Sprint 6

Sprint #2

Estimated Velocity: 6
Sprint Backlog
Story ID	Story / Task	Estimated / Hours	Actual / Hours
S1	Attach Raspberry pi, Cameras, Batteries	1
	Learn how to program motor controller	2	4
	Find power draw of circuits	1
	Figure out if an external USB bus will be needed for the cameras, and if so put them on one	1	1
S4	Build Gstreamer for raspi	2	2
	Find proper Gstreamer settings	2	8
	Write scripts to start gstreamer and check various settings.	1	2
	Find way to dynamically assign IP	1	4

## Iteration #2 Review Meeting
Unfortunately, this sprint has not gone according to plan. Research into how to properly stream from the raspi has gone way longer than expected and the robot has run into some unexpected hiccups.

## Iteration #2 Retrospective
Only managed to get the stream done. Didn't have as much time as I wanted this sprint to work on development and ran into a ton of hiccups. Hopefully I can catch up next sprint.

Sprint #3

Estimated Velocity: 3
Sprint Backlog
Story ID	Story / Task	Estimated / Hours	Actual / Hours
S3	Create Layout for settings	1	1
	Save Settings to shared preferences	1/2	1/2
	Create shared preferences wrapper	½	½

## Iteration #3 Review Meeting
I've decided to pivot the project a little bit and instead focus more on a fixed platform with a servo. As such, I'm waiting on building the robot, and instead going to work on the interface to enter the settings for the input of the streams.

## Iteration #3 Retrospective
This iteration went really smoothly. I was able to knock out the settings screen pretty smoothly. Next iteration I'll probably be able to assemble the robot which will put me back on track.

Iteration #3 Topic: Design
When I initially wrote my settings activity it was doing the writing to shared preferences. This seemed kind of bad, but seemed really bad once I wanted to start reading from shared preferences in my Render class, since it didn't seem like those modules should have any coupling at all. I then split it out into a SettingsStorage and a SettingsActivity in order to make the coupling make more sense, and separate the concerns. It also allowed me to make the settings storage effectively a singleton which will help with performance. I'm considering using something like Guice to do dependency injection to allow for me to test some of this code modularly. Maybe I'll do that next iteration.

Sprint #4
Estimated Velocity: 3
Sprint Backlog
Story ID	Story / Task	Estimated / Hours	Actual / Hours
_	Refactoring	3	4
S7	Add to shared preferences	1/2
	Read in robot controller
_	Stub out robot controller

## Iteration #4 Review Meeting
I decided since I would have a short sprint due to robotics and being out of town over spring break that I would focus on refactoring and try to eliminate some of the technical debt I've accrued.

## Iteration #4 Retrospective
Everything went smoothly. I was only able to dedicate 4 hours to refactoring but I feel like I made progress. I also added user input sanitizing and some exceptions. I should have a lot more time to commit in the final two sprints now that that robotics is over.

Iteration #4 Topic: Exceptions
I added some user exceptions in the settings screen. It's sort of hard to add more exceptions than that right now, but I think once I start programming the robot there should be more exceptions to add.